## Cover
Safety Plan
Version
Date
Status
Project
1. Participants
Last Name, First Name | Job Titile | Role |  | Responsible For
2. Quality Assurance
Role | Name | Date |  | Status
Reviewer
Approver
3. Change Record
Document Section | Change Description |  | Version | Date | Author

## General-Description
Safety Plan
1 Introducion
This template "safety plan" includes all document relevant aspects of ISO 26262. By listing the work products, the distribution of responsibilty and appointments and allocating the status, the project can effectively be setup and be tracked. At the same time the key aspects (see Figure 2 Scope of the Safety Plan) of a "DIA" and a "Safety Cases" are satisfiable. (Relevant information and input into the template provided) For the user this also offers an easy way to customize the template according to his needs. Columns and rows can be added. By using "cross-references" a parallel description with all the negative effects is avoided. Main intention is keeping key information by collecting the appropriate links and to give/collect/track status and time line.
2 Scope of the Safety Plan
The safety manager shall maintain the "Safety Plan", and monitor the progress of the safety activities against the safety plan. The aspects of a "Development Interface Agreement" (DIA) is the definition and description of the flow of all safety related development activities and work products. It shall define the interfaces between OEM and Suppliers for distributed development projects. The "Safety Case" should progressively compile the work products that are generated during the safety lifecycle. All three aspects can be combined with these work sheets and their inclosing work products.
3 Structure of the document:
1. Sheet "1_Role and Responsibilities": All involved persons and companies and roles in the project are listet and are referenced in the other sheets. 2. Sheet "2_Safety_plan": The general planing of the project is done within these sheet. A detailed description of the single rows can be found in the sheet "Description of 2_Safety_plan" 3. Sheet "3_Document_list": This is the list where all the document and work products are listed and the refering Verknäpfungen within the project are done. A detailed description of the single rows can be found in the sheet "Description of 3_Document_list" 4. Sheet "DATA": Within this sheet there are needed excel datas stored.
4 General description hints to used bakground colors:
All cells filled with grey are not to be filled out
All cells filled with yellow are not to be filled out
All cells filled with linked content
All cells Partly filled with blue are not to be filled out
All cells filled with white color are to be filled
5 Glossary
ASIL = Automotive Safety Integrity Level OU = Organisation Unit SaM = Safety Manager SaE = Safety Engineer PL = Project leader SPL = Subproject Leader R1)A2)S3)C4)I5) = Responsible, Accountable, Support, Consultant, Informative FMEA = Failure Mode & Effect Analysis FTA = Fault Tree Analysis HAZOP = Hazard and Operability study ETA = Event Tree Analysis RBD = Reliability Block Diagram

## 1_Role and Responsibilities
Safety Plan
Project Milestones
Planning and Coordination of Safety Activities
Refer to Safety plan Sheet
Organization Chart
Escalation Path
Comunication Mechanism
Problem Management
Supporting Process
Assignment of roles / persons
No. | Role | Organization | Title in Project | Responsibility |  | Name | Qualification | Contact details
1 | Project Manager (Item) | OEM | OEM Project Manager (Item) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
2 | Safety Manager (Item) | OEM | OEM Safety Manager (Item) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
3 | Project Director | OEM | OEM Project Director |  |  |  |  | Phone: Mobile: Fax: E-Mail:
4 | Project Manager (ECU) | Tier 1 Supplier | Tier 1 Supplier Project Manager (ECU) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
5 | Safety Manager (ECU) | Tier 1 Supplier | Tier 1 Supplier Safety Manager (ECU) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
6 | Quality Manager (ECU) | Tier 1 Supplier | Tier 1 Supplier Quality Manager (ECU) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
7 | R&D Manager (ECU) | Tier 1 Supplier | Tier 1 Supplier R&D Manager (ECU) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
8 | Safety Expert (ECU) (System) | Tier 1 Supplier | Tier 1 Supplier Safety Expert (ECU) (System) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
9 | Safety Expert (ECU) (HW + HW-Test) | Tier 1 Supplier | Tier 1 Supplier Safety Expert (ECU) (HW + HW-Test) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
10 | Safety Expert (ECU) (SW + SW-Test, Tool-Qualification) | Tier 1 Supplier | Tier 1 Supplier Safety Expert (ECU) (SW + SW-Test, Tool-Qualification) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
11 | Safety Expert (ECU) (Safety Analyses, HW-Metrics) | Tier 1 Supplier | Tier 1 Supplier Safety Expert (ECU) (Safety Analyses, HW-Metrics) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
12 | Configuration Manager |  | Configuration Manager |  |  |  |  | Phone: Mobile: Fax: E-Mail:
13 | Project Director |  | Project Director |  |  |  |  | Phone: Mobile: Fax: E-Mail:
14 | Safety Assessor (ECU) |  | Safety Assessor (ECU) |  |  |  |  | Phone: Mobile: Fax: E-Mail:
Change Histroy
No. | Description | Author |  |  | Date | Version
1
2
3
4
References
No. | Description | Author |  |  | Date | Version
1
2
3
4
5

## Description of 2_Safety_plan
Safety Plan
1. Description to headlines of sheet "2_Safety_plan"
No. | Number of List
Reference to standard | The refering chapter number of ISO26262
Content | Summarized content description. Partly filled with examples.
Objectives / Target | Condensed description of each objectiv/target.The content describes the requirements of the ISO 26262 standard. For the particular development project supplements or descriptions can be to added below.
Implementation of Objectives /Targets | Description and hints of the implementation in the project. Partly filled with examples.
Input documents | Document content, prerequisities or results which are needed as input information.
Output documents | Documents content or results which areoutput information Partly filled with examples.
Responsibility | The responsible for the Output document. For first approach as minimum information the resp. organisation has to be stated. There might be more than one. Partly filled with examples.
Implementation accomplishment | As far as the implementation differes from the responsible organisation it has to be stated by whom the Implementation/accomplishment relies on. There might be more than one named thus these can be named by adding rows. Partly filled with examples.
Start | Planed start of the activity in accordance of the roject plan. Partly filled with examples.
End | Planed End of the activity in accordance of the roject plan. Partly filled with examples.
Resources [h] | If appilcable Estimated working hours for Output Partly filled with examples.
Note | Space for notes. Partly filled with examples.

## 2_Safety_plan
Safety Plan
Project: ECU
#REF!
[27 empty] | #REF! | #REF!
#REF!
#REF!
No. | Reference to standard | Content | Objectives / Target | Implementation of Objectives /Targets | Mapping to Internal Work Product | Tailoring applicable? | Arguments for applying the Tailoring [see 26262-8 Support] | Input documents | Output documents | Responsibility | Implementation accomplishment | Start | End | Tier 1 Supplier Project Manager (ECU) | Tier 1 Supplier Safety Manager (ECU) | Tier 1 Supplier Quality Manager (ECU) | Tier 1 Supplier R&D Manager (ECU) | Tier 1 Supplier Safety Expert (ECU) (System) | Tier 1 Supplier Safety Expert (ECU) (HW + HW-Test) | Tier 1 Supplier Safety Expert (ECU) (SW + SW-Test, Tool-Qualification) | Tier 1 Supplier Safety Expert (ECU) (Safety Analyses, HW-Metrics) | Safety Assessor (ECU) | Development Resources [h] | Safety Assessor Resource [h] | Gesamt Resources [h] | Resource to Use | Note | Date of Note
1 |  | General
|  | Purpose | The requirements of the ISO 26262 safety standard lead to the necessity of systematically planning the activities and measures for ensuring functional safety and of naming responsible persons for the individual activities. This is part of the management tasks of the person responsible for the entire project.
|  | Procedure | The safety project plan serves to systematically plan and allocate the safety activities required and the resources necessary for its implementation. The safety plan on hand was adapted to the project. This plan is to be approved by the project management; the safety activities are to be explicitly adopted into the overall project plan in sufficient detail and the necessary resources are to be assigned to them. The safety project plan is implemented, versioned and archived for future reference by the project management. Updates and adjustments of the safety plan are also subject to versioning and documentation as in a controlled document. The updated safety project plan forms the basis for the creation of what is referred to as “safety cases”, a systematic summary of all documents necessary for proving functional safety.
2 | ISO 26262-2 | Management of functional safety
| ISO 26262-2 Clause 5 | Management of functional safety - Overall safety management
2.1 | ISO 26262-2, 5.5.1 | Organization-specific rules and processes for functional safety | Objective acc. the standard ISO 26262-2 (clause: 5.4.2.2): The organization shall institute, execute and maintain organization-specific rules and processes to comply with the requirements of ISO 26262. NOTE Such organization-specific rules and processes can include the creation and maintenance of a generic safety plan and process description. | e.g. generic process of functional saftey |  |  |  |  | Organization-specific rules and processes for functional safety | OEM Project Manager (Item) | OEM Project Director
2.2 | ISO 26262-2, 5.5.2 | Evidence of competence | Objective acc. the standard ISO 26262-2 (clause 5.4.3.1): The organization shall ensure that the persons involved in the execution of the safety lifecycle have a sufficient level of skills, competences and qualifications corresponding to their responsibilities. (Knowledge in safety technology, safety standards, etc.) | Client's safety management training program, etc. ETSS analysis results, training certificate, Client qualification, office organization, etc. |  | No |  |  | Evidence of competence
2.3 | ISO 26262-2, 5.5.3 | Evidence of quality management | Objective acc. the standard ISO 26262-2 (clause 5.4.4.1): The organizations involved in the execution of the safety lifecycle shall have an operational quality management system complying with a quality management standard, such as ISO/TS 16949, ISO 9001, or equivalent. | See Project Plan |  | No |  | ISO 9001 certificate, ISO TS 16949 certificate, Audit reports, | Evidence of quality management | [17 empty] | ISO 16949
2.3 | ISO 26262-2, 5.5.4 | Identified safety anomaly | Objective acc. the standard ISO 26262-2 (clause 5.4.3): |  |  | No |  | Safety anomaly | Identified Safety anomaly report | [17 empty] | ISO 16949
| ISO 26262-2 Clause 6 | Management of functional safety - Safety management during the concept phase and the product development
2.4 | ISO 26262-2, 6.5.1,6.5.2 | Impact Analysis | Objective acc. the standard ISO 26262-2 (clause 6.4.3 and clause 6.4.4) |  |  | No |  | Customer Project Requirements or Internal Project Requirements | Impact Analysis Report
2.5 | ISO 26262-2, 6.5.3 | Safety plan | Objective acc. the standard ISO 26262-2 (clause 6.4.3.4): The safety plan shall either be a) referenced in the project plan, or b) included in the project plan, such that the safety activities are distinguishable Objective for Item under developement: Project management for the safety activities • Planning of safety activities with regard to time and resources • Defining responsibilities • Requesting the results of the work packages defined in the safety plan from those responsible in a timely manner • Updating the safety plan with regard to changes in dates, resources, work packages • Determining the safety-relevant release stECU up to series launch |  |  | No |  | Project plan, System concept draft, System concept review, DIA, Timeline with milestones for prototypes, Required documents according to ISO26262 | Safety Plan
2.6 | ISO 26262-2, 6.5.4 | Safety Case | Objective acc. the standard ISO 26262-2: (clause 6.4.6.1) This requirement shall be complied with for items that have at least one safety goal with an ASIL (A), B, C or D: a safety case shall be developed in accordance with the safety plan. (clause 6.4.6.2) The safety case should progressively compile the work products that are generated during the safety lifecycle. |  |  | No |  | Document list, Available work products, protocols, meeting minutes... | Safety Case
2.7 | ISO 26262-2, 6.5.5 | Functional safety assessment plan | Objective acc. the standard ISO 26262-2: (clause 6.4.9.1) A functional safety assessment shall be carried out for items, where the highest ASIL of the item's safety goals is ASIL (B), C, or D. (clause 6.4.9.2) A functional safety assessment shall be planned in accordance with 6.4.3.3 and 6.4.3.5 i). EXAMPLE Agenda for a functional safety assessment given in Annex E. |  |  | No |  | Work products required by the safety plan; safety processes; | Functional safety assessment plan
2.8 | ISO 26262-2, 6.5.5 | Confirmation measure reports | Objective acc. the standard ISO 26262-2: (clause 6.4.7.1) The confirmation measures specified in Table 1, ISO 26262-2 shall be performed, in accordance with the required level of independency. Remark: A confirmation review includes the checking of correctness with respect to formality, contents, adequacy and completeness regarding the requirements of ISO 26262. ONLY Organization and planning of confirmation reviews |  |  | No |  | Table of confirmation measures, Assessment report, Audit report | Confirmation measures reports
2.9 | ISO 26262-2, 6.5.6 | Release for production report | Objective acc. the standard ISO 26262-2(clause 6.4.13) The requirements of ISO 26262-2, clause 6.4.13 shall be fulfilled. The objective of this clause is to specify the release for production criteria at the completion of the item development. The release for production confirms that the item complies with the requirements for functional safety at the vehicle level. | Tier1 shall state the release for production in order to confirm that the item complies with the requirements for functional safety. |  | No |  | Safety plan, Safety case, Project Plan, | Release for production report
| ISO 26262-2 Clause 7 | Management of functional safety - Safety management after the item's release for production
2.10 | ISO 26262-2, 7.5.1 | Evidence of safety management regarding production, operation, service and decommissioning | Objective acc. the standard ISO 26262-2: (clause 7.4.2): The objective of this clause is to define the responsibilities of the organizations and persons responsible for functional safety after the item's release for production. This relates to the general activities for ensuring the required functional safety of the item during the lifecycle sub phases after the release for production. |  |  | No |  | Evidence of quality management | Suppliers Safety Management and support processes after SOP
3 | ISO 26262-3
| ISO 26262-3 Clause 5 | Item definition
3.1 | ISO 26262-3, 5.5.1 | Item definition | Objective acc. the standard ISO 26262-3(clause 5.5.1): The first objective is to define and describe the item, its dependencies on, and interaction with, the environment and other items. The second objective is to support an adequate understanding of the item so that the activities in subsequent phases can be performed. Remark: Description of planed function. On the basis of a represented system design a project order could be released. | A description of the item with the corresponding subsystems XYZ: e.g.: steering angle sensor, torque sensor of steering wheel , Shift by wire shall be prepared. |  | No |  | System concept draft, System concept review, Item definition | Item definition
#REF!
| ISO 26262-3 Clause 6 | Hazard analysis and risk assessment (System and subsystem)
3.2 | ISO 26262-3, 6.5.1 | Hazard analysis and risk assessment | Objective acc. the standard ISO 26262-3: The objective of the hazard analysis and risk assessment is to identify and to categorise the hazards that malfunctions in the item can trigger and to formulate the safety goals related to the prevention or mitigation of the hazardous events, in order to avoid unreasonable risk. |  |  | No |  | Existing H&R, Item definition Impact analysis, Relevant information of other subsystems, | Hazard analysis and risk assessment
3.3 | ISO 26262-3, 6.5.2 | Safety goals | Objective acc. the standard ISO 26262-3: A safety goal shall be determined for each hazardous event with an ASIL evaluated in the hazard analysis. | The existing safety goals shall be checked by Tier1 / Independent Reviewer. |  | No |  | Existing safety goals, | Safety goals
3.4 | ISO 26262-3, 6.5.3 | Verification report of the hazard analysis and risk assessment and the safety goals. | Objective acc. the standard ISO 26262-3: The hazard analysis, risk assessment and the safety goals shall be verified in accordance with ISO 26262-8:2018, Clause 9, to show their: a) completeness with regard to situations and hazards; b) compliance with the item definition; c) consistency with related hazard analyses and risk assessments; d) completeness of the coverage of the hazardous events; and e) consistency of the assigned ASILs with the corresponding hazardous events. |  |  | No |  | Existing review report of the Hazard analysis and risk assessment and the safety goals. | Verification review report of the hazard analysis and risk assessment and the safety goals.
| ISO 26262-3 Clause 7 | Functional safety concept
3.5 | ISO 26262-3, 7.5.1 | Functional safety concept | Objective acc. the standard ISO 26262-3: The objective of the functional safety concept is to derive the functional safety requirements, from the safety goals, and to allocate them to the preliminary architectural elements of the item, or to external measures. |  |  | No |  | Item definition H&R, Safety goals, Technik Komponenten Lastenheft, SANF_Sicherheitsanforderungen | Functional safety concept (including safety architecture)
3.6 | ISO 26262-3, 7.5.2 | Verification report of the functional safety concept | Objective acc. the standard ISO 26262-3: The functional safety concept shall be verified in accordance with ISO 26262-8:2018, Clause 9, to show a) its consistency and compliance with the safety goals; and b) its ability to mitigate or avoid the hazardous events. |  |  | No |  | Functional safety concept in latest version | Review report of the functional safety concept
4 | ISO 26262-4 | Product development at the system level
| ISO 26262-4 Clause 5 | Initiation of product development at the system level
4.1 | ISO 26262-4, 5.5.2 | Safety plan (refined) | The safety activities for the product development at the system level shall be planned including determination of appropriate methods and measures during design and integration. The validation activities shall be planned. The functional safety assessment activities for the product development at the system level shall be planned. The tailoring of the lifecycle for product development at system level shall be performed in accordance with ISO 26262-2, and based on the reference phase model. NOTE The project plan can be used to provide the relationship between the individual subphases of product development at the system level and the hardware and software development phases. This can include the integration stECU at each level. |  |  | No |  | Safety plan (see No. 2.4) | Safety plan (refined)
4.2 | ISO 26262-4, 5.5.3 | Item integration and testing plan | Objective acc. the standard ISO 26262-4: The objective of the initiation of the product development at the system level is to determine and plan the functional safety activities during the individual sub phases of system development. This also includes the necessary supporting processes described in ISO 26262-8. This planning of system-level safety activities will be included in the safety plan. |  |  | No |  | Functional safety concept, Safety plan, Project plan | Item integration and testing plan
4.3 | ISO 26262-4, 5.5.4 | Validation plan | Objective acc. the standard ISO 26262-4: The validation activities shall be planned. Objective for item under developement: Safety validation on vehicle level. The safety validation of the overall system under developement will be carried out on vehicle level. (Evidence of system safety). This includes testing of controllability, measuring of the fault tolerance time of subsystems etc. | Tier1 shall support the system validation of the under developement. | Tier1 shall support the system validation of the under developement. | No |  | Functional safety concept, Safety plan, Project plan | Validation plan
| ISO 26262-4 Clause 6 | Technical safety concept
4.4 | ISO 26262-4, 6.5.1 | Technical safety requirements specification | Objective acc. the standard ISO 26262-4: The first objective of this sub phase is to specify the technical safety requirements. The technical safety requirements specification refines the functional safety concept, considering both the functional concept and the preliminary architectural assumptions (see ISO 26262-3). The second objective is to verify through analysis that the technical safety requirements comply with the functional safety requirements. Objective for item under developement: Tier1 is responsible to specify the technical safety requirements for the item under developement with the associated subsystems LWS, TMP, SBW, BLS, FUS |  |  | No |  | H&R, Safety goals, Functional safety requirements, Technical safety requirements | Technical safety requirements specifications
4.5 | ISO 26262-4, 6.5.2 | Technical safety concept | Objective acc. the standard ISO 26262-4: The first objective of this sub phase is to develop the system design and the technical safety concept that comply with the functional requirements and the technical safety requirements specification of the item. The second objective of this sub phase is to verify that the system design and the technical safety concept comply with the technical safety requirements specification. | Tier1 is responsible for the technical safety concept. | Tier1 is responsible for the technical safety concept. | No |  | Technical safety concept of the item, Technical safety requirements specification, Item integration and testing plan | Technical safety concept
4.6 | ISO 26262-4, 6.5.3 | System design specification | Objective acc. the standard ISO 26262-4: The system design shall be based on the functional concept, the preliminary architectural assumptions and the technical safety requirements. The consistency of the preliminary architectural assumptions in ISO 26262-3:2018, 8.3.2 and the preliminary architectural assumptions in this sub phase shall be ensured. |  |  | No |  | Technical safety concept of the item, Technical safety requirements specification | System design specification
4.7 | ISO 26262-4, 6.5.4 | Hardware-software interface specification (HSI) | Objective acc. the standard ISO 26262-4: The HSI specification shall specify the hardware and software interaction and be consistent with the technical safety concept. The HSI specification shall include the component's hardware devices that are controlled by software and hardware resources that support the execution of software. |  |  | No |  | Technical safety concept of the item, Technical safety requirements specification | Hardware-software interface specification (HSI)
4.8 | ISO 26262-4, 6.5.5 | Specification of requirements for production, operation, service and decommissioning | Objective acc. the standard ISO 26262-4: The requirements for production, operation, service and decommissioning, identified during the system design, shall be specified (see ISO 26262-7). These include: a) the assembly instructions requirements; b) the safety-related special characteristics; c) the requirements dedicated to ensure proper identification of systems or elements; EXAMPLE 1 Labelling of elements. d) the verification methods and measures for production; e) the service requirements including diagnostic data and service notes; and f) the decommissioning requirements Objective for item under developement: |  |  | No |  | Technical safety requirements specification of the subsystem SSSPR | Specification of requirements for production. Specification of operation, service, and decommissioning
4.9 | ISO 26262-4, 6.5.6 | System verification report | Objective acc. the standard ISO 26262-4: The system design shall be verified for compliance and completeness with regard to the technical safety concept using the verification methods listed in Table 3. Table 1 and ISO 26262-9:2018, Clause 8. |  |  | No |  | System design specification System-FMEDA Functional safety concept, Technical safety concept, Block diagram | System verification report (refined)
4.10 | ISO 26262-4, 6.5.7 | Safety analysis reports FMEA | Objective acc. the standard ISO 26262-4: Safety analyses on the system design to identify the causes of systematic failures and the effects of systematic faults shall be applied in accordance with Table 1 ISO 26262-4 and ISO 26262-9:2018, Clause 8. |  |  | No |  | System-FMEA, | Safety analysis report
4.11 | ISO 26262-4, 6.5.7 | Safety analysis reports FTA | Objective acc. the standard ISO 26262-4: Safety analyses on the system design to identify the causes of systematic failures and the effects of systematic faults shall be applied in accordance with Table 1 ISO 26262-4 and ISO 26262-9:2018, Clause 8. |  |  | No |  | System-FTA | Safety analysis report
| ISO 26262-4 Clause 7 | Item integration and testing
4.12 | ISO 26262-4, 7.5.1 | Item integration and testing plan (refined) | Objective acc. the standard ISO 26262-4: The integration and testing phase comprises three phases and two primary goals as described below: the first phase is the integration of the hardware and software of each element that the item comprises. The second phase is the integration of the elements that comprise an item to form a complete system. The third phase is the integration of the item with other systems within a vehicle and with the vehicle itself. The first objective of the integration process is to test compliance with each safety requirement in accordance with its specification and ASIL classification. The second objective is to verify that the “System design” covering the safety requirements [see Clause 7 (System design)] are correctly implemented by the entire item. |  |  | No |  | Safety goals, Functional safety concept, Technical safety concept, System design specification, | Item integration and testing plan (refined)
|  |  |  | Tier1 is responsible for testing at system level. | Tier1 is responsible for testing at system level.
|  |  |  | OEM is responsible for testing at vehicle level. | OEM is responsible for testing at vehicle level.
4.13 | ISO 26262-4, 7.5.1 | Integration and test strategy | Objective acc. the standard ISO 26262-4: To demonstrate that the system design is compliant with the functional and technical safety requirements, integration testing activities shall be performed in accordance with ISO 26262-8:2018, Clause 9. NOTE The following test goals are addressed in Tables 4 to 18: a) the correct implementation of functional safety and technical safety requirements; b) the correct functional performance, accuracy and timing of safety mechanisms; c) the consistent and correct implementation of interfaces; d) the effectiveness of a safety mechanism's diagnostic or failure coverage; and e) the level of robustness. |  |  | No |  | Safety goals, Functional safety concept, Technical safety concept, System design specification, Item integration and testing plan | Integration testing specification(s)
4.18 | ISO 26262-4, 7.5.2 | Integration and test report | Objective acc. the standard ISO 26262-4: Testing reports resulting from the requirements from ISO 26262-4 | Tier1 is responsible for testing at system level. |  | No |  | Safety goals, Functional safety concept, Technical safety concept, System design specification, Item integration and testing plan, Integration testing specification(s) | Integration testing reports(s)
OEM is responsible for testing at vehicle level.
| ISO 26262-4 Clause 9 | Safety validation
4.19 | ISO 26262-4, 8.5.1 | Validation plan (refined) | Objective acc. the standard ISO 26262-4: The first objective is to provide evidence of compliance with the safety goals and that the functional safety concepts are appropriate for the functional safety of the item. The second objective is to provide evidence that the safety goals are correct, complete and fully achieved at the vehicle level. |  |  | No |  | Safety goals, Functional Safety Concept, Technical safety concept | Validation plan (refined)
|  |  |  | Tier1 is responsible for testing at system level. | Tier1 is responsible for testing at system level.
|  |  |  | OEM is responsible for testing at vehicle level. | OEM is responsible for testing at vehicle level.
4.20 | ISO 26262-4, 8.5.1 | Validation Specification including safety validation environment description | Objective acc. the standard ISO 26262-4: Validation report resulting from requirements 9.4.3 and 9.4.4 Objective for item under developement after tailoring: | Tier1 is responsible for testing at system level. |  | No |  | Validation plan, Safety goals, Functional Safety Concept, Technical safety concept | Validation report
OEM is responsible for testing at vehicle level.
4.20 | ISO 26262-4, 8.5.2 | Validation report | Objective acc. the standard ISO 26262-4: Validation report resulting from requirements 9.4.3 and 9.4.4 Objective for item under developement after tailoring: | Tier1 is responsible for testing at system level. |  | No |  | Validation plan, Safety goals, Functional Safety Concept, Technical safety concept | Validation report
OEM is responsible for testing at vehicle level.
5 | ISO 26262-5 | Product development at the hardware level
| ISO 26262-5 Clause 5 | Initiation of product development at the hardware level
5.1 | ISO 26262-5, 5.5.1 | Safety plan (refined) | Objective acc. the standard ISO 26262-5: The objective of the initiation of the product development for the hardware is to determine and plan the functional safety activities during the individual sub phases of hardware development. This also includes the necessary supporting processes described in ISO 26262-8. This planning of hardware-specific safety activities is included in the safety plan (see ISO 26262-2:2018, 6.4.3, and ISO 26262-4:2018, 5.4).. | Tier1 is responsible for the safety plan. |  | No |  | Project plan, Safety plan, Testing plan, | Safety plan (refined)
| ISO 26262-5 Clause 6 | Specification of hardware safety requirements
5.2 | ISO 26262-5, 6.5.1 | Hardware safety requirements specification (including test and qualification criteria) | Objective acc. the standard ISO 26262-5: The first objective of this clause is to specify the hardware safety requirements. They are derived from the technical safety concept and system design specification. The second objective is to verify that the hardware safety requirements are consistent with the technical safety concept and the system design specification. A further objective of this phase is to detail the hardware-software interface (HSI) specification initiated in ISO 26262-4:2018, Clause 7. Objective for item under developement after tailoring: The hardware safety requirements specification with test and qualification criteria shall be stated. |  |  | No |  | Safety plan, Technical safety concept, System design specification, hardware-software interface specification | Hardware safety requirements specification (including test and qualification criteria)
5.3 | ISO 26262-5, 6.5.2 | Hardware-software interface specification (refined) | Objective acc. the standard ISO 26262-5: |  |  | No |  | Safety plan, Technical safety concept, System design specification, hardware-software interface specification | Hardware-software interface specification (refined)
5.4 | ISO 26262-5, 6.5.3 | Hardware safety requirements verification report | Objective acc. the standard ISO 26262-5: The hardware safety requirements shall be verified in accordance with ISO 26262-8:2018, Clauses 6 and 9, in order to provide evidence of their: a) consistency with the technical safety concept, the system design specification and the hardware specifications; b) completeness with respect to the technical safety requirements allocated to the hardware element; c) consistency with the relevant software safety requirements; and d) correctness and accuracy. | The verification report of the HW safety requirements shall be carried out by Tier1 |  | No |  | Safety plan, Technical safety concept, System design specification, | Hardware safety requirements verification report
| ISO 26262-5 Clause 7 | Hardware design
5.5 | ISO 26262-5, 7.5.1 | Hardware design specification | Objective acc. the standard ISO 26262-5: The first objective of this clause 7 is to design the hardware in accordance with the system design specification and the hardware safety requirements. 7.4.1 Hardware architectural design 7.4.2 Hardware detailed design |  |  | No |  | Hardware safety requirements specification, System design specification, Safety plan, Sketch | Hardware design specification
5.6 | ISO 26262-5, 7.5.2 | Hardware safety analysis report | Objective acc. the standard ISO 26262-5: Safety analyses on hardware design to identify the causes of failures and the effects of faults shall be applied in accordance with Table 2 and ISO 26262-9:2018, Clause 8. 7.4.3 Safety analyses Objective for item under developement after tailoring: One subsystem of the item is ASIL-D rated and table 2 of ISO 26262-5 is applied. Therefore a deductive analysis as for example a FTA and a inductive analysis as for example FMEDA shall be carried out. Failure rates and failure models for the FMEDA shall be stated. |  |  | No |  | Hardware safety requirements specification, System design specification, Safety plan | Hardware safety analysis report
5.7 | ISO 26262-5, 7.5.3 | Hardware design verification report | Objective acc. the standard ISO 26262-5: The hardware design shall be verified in accordance with ISO 26262-8, Clause 9, for compliance and completeness with respect to the hardware safety requirements. To achieve this, the methods listed in Table 3 shall be considered Objective for item under developement after tailoring: |  |  | No |  | Hardware safety requirements specification, System design specification, Safety plan, Schematic sketch | Hardware design verification report
5.8 | ISO 26262-5, 7.5.4 | Specification of requirements related to production, operation, service and decommissioning | Objective acc. the standard ISO 26262-5: Safety-related special characteristics shall be specified if safety analyses have shown them to be relevant. Attributes of safety-related special characteristics shall include: a) the verification measures for production and operation; and b) the acceptance criteria for these measures. |  |  | No |  | Hardware safety requirements specification, System design specification, Safety plan, Schematic sketch, HW-Design | Specification of requirements related to production, operation, service and decommissioning (Assembly instruction)
| ISO 26262-5 Clause 8 | Evaluation of the hardware architectural metrics
5.9 | ISO 26262-5, 8.5.1 | Analysis of the effectiveness of the architecture of the item to cope with the random hardware failures | Objective acc. the standard ISO 26262-5: The objective of this clause is to evaluate the hardware architecture of the item against the requirements for fault handling as represented by the hardware architectural metrics. This requirement applies to ASIL (B), C, and D of the safety goal. Remark: For each safety goal, a quantitative target value shall be derived from Table 4, ISO 26262-5 e.g.: Single-point fault metric for ASIL D: ≥ 99% Latent-fault metric for ASIL D: ≥ 90% |  |  | No |  | Schematic, Hardware safety requirements specification, Hardware design specification, Hardware safety analysis report | Analysis of the effectiveness of the architecture of the item to cope with the random hardware failures
5.10 | ISO 26262-5, 8.5.2 | Verification review report of evaluation of the effectiveness of the architecture of the item to cope with the random hardware failures | Objective acc. the standard ISO 26262-5: This requirement applies to ASIL (B), C, and D of the safety goal. A verification review of the result of the applied methods in 8.4.7 and 8.4.8 shall be performed in order to provide evidence of its technical correctness and completeness. |  |  | No |  | FTA, Metrics, Schematic, Hardware safety requirements specification, Hardware design specification, Hardware safety analysis report | Review report of evaluation of the effectiveness of the architecture of the item to cope with the random hardware failures
ISO 26262-5 Clause 9
5.11 | ISO 26262-5, 9.5.1 | Analysis of safety goal violations due to random hardware failures | Objective acc. the standard ISO 26262-5: This requirement applies to ASIL (B), C and D of the safety goal. The objective of the requirements in this clause is to make available criteria that can be used in a rationale that the residual risk of a safety goal violation, due to random hardware failures of the item, is sufficiently low. Objective for item under developement after tailoring: Tier1 is responsible for Evaluation of Probabilistic Metric for random Hardware Failures (PMHF). |  |  | No |  | Hardware safety analysis report, Hardware safety requirement specification, Hardware design specification | Analysis of safety goal violations due to random hardware failures
5.12 | ISO 26262-5, 9.5.2 | Specification of dedicated measures for hardware (if needed) | Objective acc. the standard ISO 26262-5: Objective for item under developement after tailoring: |  |  | No |  | Hardware safety analysis report, Hardware safety requirement specification, Hardware design specification | Specification of dedicated measures for hardware (if needed)
|  |  |  | In responsibility of Tier1. | In responsibility of Tier1.
5.13 | ISO 26262-5, 9.5.3 | Verification review report of evaluation of safety goal violations due to random hardware failures | Objective acc. the standard ISO 26262-5: This requirement applies to ASIL (B), C, and D of the safety goal. A verification review of the analysis resulting from the set of requirements 9.4.2 or 9.4.3 shall be performed in order to provide evidence of its technical correctness and completeness in accordance with ISO 26262-8:2018, Clause 9. |  |  | No |  | Hardware safety analysis report, Hardware safety requirement specification, Hardware design specification | Review report of evaluation of safety goal violations due to random hardware failures
| ISO 26262-5 Clause 10 | Hardware integration and testing
5.14 | ISO 26262-5, 10.5.1 | Hardware integration and verification specification | Objective acc. the standard ISO 26262-5: The objective of this clause is to ensure, by testing, the compliance of the developed hardware with the hardware safety requirements. The requirements in 10.4.1 to 10.4.6 apply to the hardware of an element NOTE If ASIL decomposition is applied, as defined in ISO 26262-9:2018, Clause 5, the corresponding integration activities of the decomposed elements, and the subsequent activities, are applied at the ASIL before decomposition. Objective for item under developement after tailoring: Test cases shall be defined by Tier1 (in collaboration with OEM if necessary). The hardware testing activities shall verify the completeness and correctness of the implementation of the safety mechanisms with respect to the hardware safety requirements. |  |  | No |  |  | Hardware integration and testing report
5.15 | ISO 26262-5, 10.5.2 | Hardware integration and verification report | Objective acc. the standard ISO 26262-5: The objective of this clause is to ensure, by testing, the compliance of the developed hardware with the hardware safety requirements. The requirements in 10.4.1 to 10.4.6 apply to the hardware of an element NOTE If ASIL decomposition is applied, as defined in ISO 26262-9:2018, Clause 5, the corresponding integration activities of the decomposed elements, and the subsequent activities, are applied at the ASIL before decomposition. Objective for item under developement after tailoring: Test cases shall be defined by Tier1 (in collaboration with OEM if necessary). The hardware testing activities shall verify the completeness and correctness of the implementation of the safety mechanisms with respect to the hardware safety requirements. |  |  | No |  |  | Hardware integration and testing report
6 | ISO 26262-6 | Product development at the software level
| ISO 26262-6 Clause 5 | Initiation of product development at the software level
6.1 | ISO 26262-6, 5.5.1 | Safety plan (refined) | Objective acc. the standard ISO 26262-6: The objective of this sub-phase is to plan and initiate the functional safety activities for the sub-phases of the software development. The software development sub-phases and supporting processes are initiated by determining the appropriate methods in order to comply with the requirements and their respective ASIL. The methods are supported by guidelines and tools, which are determined and planned for each sub-phase and supporting process. The requirements in 5.4.1 to 5.4.7 apply. |  |  | No |  | Project plan, Safety plan, Technical safety concept, System design spec. Item integration and testing plan | Safety plan (refined)
6.2 | ISO 26262-6, 5.5.1 | Software verification plan | Objective acc. the standard ISO 26262-6: The objective of this sub-phase is to plan and initiate the functional safety activities for the sub-phases of the software development. The requirements in 5.4.1 to 5.4.5and 5.4.7 apply. |  |  | No |  | Project plan, Safety plan, Technical safety concept, System design spec. Item integration and testing plan | Software verification plan
6.3 | ISO 26262-6, 5.5.1 | Documentation of the software development environment | Objective acc. the standard ISO 26262-6: Criteria shall be considered when selecting a suitable modelling or programming language To support the correctness of the design and implementation, the design and coding guidelines for the modelling, or programming languages, shall address the topics listed in Table 1. The requirements in 5.4.6 and 5.4.7 apply. |  |  | No |  | Project plan, Safety plan, Technical safety concept, System design spec. Item integration and testing plan | Design and coding guidelines for modelling and programming languages
| ISO 26262-6 Clause 6 | Specification of software safety requirements
6.5 | ISO 26262-6, 6.5.1 | Software safety requirements specification | Objective acc. the standard ISO 26262-6: The first objective of this sub-phase is to specify the software safety requirements. They are derived from the technical safety concept and the system design specification. The requirements in 6.4.1 to 6.4.3 and 6.4.5 apply. |  |  | No |  | Technical safety concept, System design specification, | Software safety requirements specification
6.6 | ISO 26262-6, 6.5.2 | Hardware-software interface specification (refined) | Objective acc. the standard ISO 26262-6: The second objective is to detail the hardware-software interface requirements initiated in ISO 26262-4:2018, Clause 7. The requirements in 6.4.4 apply. |  |  | No |  | Hardware-software interface specification, | Hardware-software interface specification (refined)
6.7 | ISO 26262-6, 6.5.3 | Software verification report | Objective acc. the standard ISO 26262-6: The third objective is to verify that the software safety requirements and the hardware-software interface requirements are consistent with the technical safety concept and the system design specification. The requirements in 6.4.6 and 6.4.7 apply. |  |  | No |  | Technical safety concept, System design specification, | Software verification report
| ISO 26262-6 Clause 7 | Software architectural design
6.8 | ISO 26262-6, 7.5.1 | Software architectural design specification | Objective acc. the standard ISO 26262-6: The first objective of this sub-phase is to develop a software architectural design that realizes the software safety requirements. The second objective of this sub-phase is to verify the software architectural design. The requirements in 7.4.1 to 7.4.6, 7.4.9, 7.4.10, 7.4.14, 7.4.15 and 7.4.17 apply. |  |  | No |  | hardware-software interface specification, software safety requirements specification, software verification plan (refined), software verification report | Software architectural design specification
6.9 | ISO 26262-6, 7.5.2 | Safety analysis report | Objective acc. the standard ISO 26262-6: Safety analysis shall be carried out at the software architectural level in accordance withISO 26262-9:2018, Clause 8, in order to: - identify or confirm the safety-related parts of the software; and - support the specification and verify the efficiency of the safety mechanisms. The requirements in 7.4.13 applied. |  |  | No |  | hardware-software interface specification, software safety requirements specification, software verification plan (refined), software verification report | Safety analysis report
6.10 | ISO 26262-6, 7.5.3 | Dependent failures analysis report | Objective acc. the standard ISO 26262-6: An analysis of dependent failures in accordance with ISO 26262-9:2018, Clause 7, shall be carried out if the implementation of software safety requirements relies on freedom from interference or sufficient independence between software components. The requirements in 7.4.12 apply. |  |  | No |  | hardware-software interface specification, software safety requirements specification, software verification plan (refined), software verification report | Dependent failures analysis report
6.11 | ISO 26262-6, 7.5.4 | Software verification report | Objective acc. the standard ISO 26262-6: The software architectural design shall be verified in accordance with ISO 26262-8:2018, Clause 9, and by using the software architectural design verification methods listed in Table 6. The requirements in 7.4.18 apply. |  |  | No |  | software verification report, | Software verification report (refined)
| ISO 26262-6 Clause 8 | Software unit design and implementation
6.12 | ISO 26262-6, 8.5.1 | Software unit design specification | Objective acc. the standard ISO 26262-6: The first objective of this sub-phase is to specify the software units in accordance with the software architectural design and the associated software safety requirements. The requirements in 8.4.2 to 8.4.5 apply. |  |  | No |  | software verification plan, software architectural design specification, software safety requirements specification, software verification report | Software unit design specification
6.13 | ISO 26262-6, 8.5.2 | Software unit implementation | Objective acc. the standard ISO 26262-6: The second objective of this sub-phase is to implement the software units as specified. The requirements in 8.4.5 apply. |  |  | No |  | software verification plan, software architectural design specification, software safety requirements specification, software verification report | Software unit implementation
| ISO 26262-6 Clause 9 | Software unit testing
6.14 | ISO 26262-6, 9.5.1 | Software verification plan (refined) | Objective acc. the standard ISO 26262-6: The objective of this sub-phase is to demonstrate that the software units fulfil the software unit design specifications and do not contain undesired functionality. The requirements in 9.4.2 to 9.4.6 apply. |  |  | No |  | Software verification plan | Software verification plan (refined)
6.15 | ISO 26262-6, 9.5.1 | Software verification specification | Objective acc. the standard ISO 26262-6: Software unit testing shall be planned, specified and executed in accordance with ISO 26262-8:2018, Clause 9. The requirements in 9.4.2 and 9.4.4 to 9.4.5 apply. |  |  | No |  | hw-sw interface specification, software verification plan, software unit design specification, software unit implementation, sw verification report | Software verification specification
6.16 | ISO 26262-6, 9.5.2 | Software verification report (refined) | Objective acc. the standard ISO 26262-6: The requirements in 9.4.2 apply. |  |  | No |  | software verification report, | Software verification report (refined)
| ISO 26262-6 Clause 10 | Software integration and testing
6.17 | ISO 26262-6, 10.5.1 | Software verification plan (refined) | Objective acc. the standard ISO 26262-6: The first objective of this sub-phase is to integrate the software elements. The second objective of this sub-phase is to demonstrate that the software architectural design is realized by the embedded software. The requirements in 10.4.1 to 10.4.6 and 10.4.8 apply. |  |  | No |  | software verification plan | Software verification plan (refined)
6.18 | ISO 26262-6, 10.5.1 | Software verification specification (refined) | Objective acc. the standard ISO 26262-6: The requirements in 10.4.2, 10.4.4, 10.4.5, 10.4.7 and 10.4.8 apply. |  |  | No |  | software verification specification | Software verification specification (refined)
6.19 | ISO 26262-6, 10.5.3 | Embedded software | Objective acc. the standard ISO 26262-6: The planning of the software integration shall describe the stECU for integrating the individual software units hierarchically into software components until the embedded software is fully integrated, and shall consider: a) the functional dependencies that are relevant for software integration; and b) the dependencies between the software integration and the hardware-software integration. The requirements in 10.4.1 apply. |  |  | No |  |  | Embedded software
6.20 | ISO 26262-6, 10.5.3 | Software verification report (refined) | Objective acc. the standard ISO 26262-6: The requirements in 10.4.2 apply. |  |  | No |  | software verification report, | Software verification report (refined)
| ISO 26262-6 Clause 11 | Verification of software safety requirements
6.21 | ISO 26262-6, 11.5.1 | Software verification plan (refined) | Objective acc. the standard ISO 26262-6: The objective of this sub-phase is to demonstrate that the embedded software fulfils the software safety requirements. The requirements in 11.4.1 to 11.4.3 apply. |  |  | No |  | software verification plan | Software verification plan (refined)
6.22 | ISO 26262-6, 11.5.1 | Software verification specification (refined) | Objective acc. the standard ISO 26262-6: The requirements in 11.4.1 to 11.4.3 apply. |  |  | No |  | software verification specification | Software verification specification (refined)
6.23 | ISO 26262-6, 11.5.2 | Software verification report (refined) | Objective acc. the standard ISO 26262-6: The requirements in 11.4.1 to 11.4.4 apply. |  |  | No |  | software verification report, | Software verification report (refined)
C | ISO 26262-6, Annex C | Software configuration
C.1 | C.5.1 | Configuration data specification | The configuration data shall be specified to ensure the correct usage of the configurable software during the safety lifecycle. The ASIL of the configuration data shall equal the highest ASIL of the configurable software by which it is used. |  |  | No
C.2 | C.5.2 | Calibration data specification | The calibration data associated with software components shall be specified to ensure the correct operation and expected performance of the configured software. |  |  | No
C.4 | C.5.3 | Configuration data | Objective acc. the standard ISO 26262-6 / C |  |  | No
C.5 | C.5.4 | Calibration data | The ASIL of the calibration data shall equal the highest ASIL of the software safety requirements it can violate. |  |  | No
C.6 | C.5.5 | Software verification plan (refined) | Objective acc. the standard ISO 26262-7: |  |  | No
C.7 | C.5.5 | Verification specification | The verification of the calibration data shall be planned, specified and executed in accordance with ISO 26262-8:2018, Clause 9. The verification of calibration data shall examine whether the calibration data is within its specified boundaries. |  |  | No
C.8 | C.5.6 | Verification report | Objective acc. the standard ISO 26262-6 / C |  |  | No
C.8 | C.5.7 | Software architectural design specification(refined) | Objective acc. the standard ISO 26262-6 / C.4.10 |  |  | No
C.8 | C.5.8 | Documentation of the (refined) | Objective acc. the standard ISO 26262-6 / C.4.1-C.4.11 |  |  | No
7 | ISO 26262-7 | Production, operation, service and decommission
| ISO 26262-7 Clause 5 | Planning for production, operation, service and decommission
7.1 | ISO 26262-7, 5.5.1 | Safety-related content of the production plan | Objective acc. the standard ISO 26262-7: The first objective of this clause is to develop and maintain a production process for safety-related elements or items that are intended to be installed in road vehicles. The second objective is to achieve functional safety during the production process by the relevant manufacturer or the person or organisation responsible for the process (vehicle manufacturer, supplier, sub supplier, etc.). Objective for item under developement after tailoring: Production plan of the item. |  |  | No |  | · Specification of requirements related to operation, service and decommissioning, · Release for production report, · Specification of dedicated measures for hardware in accordance with ISO 26262-5:2018, 9.5.2 | Safety-related content of the production plan
7.2 | ISO 26262-7, 5.5.2 | Safety-related content of the production control plan, including test plan | Objective acc. the standard ISO 26262-7: |  |  | No |  | Safety related content of the production plan | Safety-related content of the production control plan
7.3 | ISO 26262-7, 5.5.3 | Producibility requirements specification | Objective acc. the standard ISO 26262-7: Objective for item under developement after tailoring: Shall be done during HW development. |  |  | No |  |  | Producibility requirements specification
7.4 | ISO 26262-7, 5.5.4 | Production process capability report | Objective acc. the standard ISO 26262-7: | Tier1 shall plan and carry out an assessment for capability of the production process according an ASIL D subsystem. |  | No |  | Safety-related content of the production plan, Safety-related content of the production control plan, Control measure report | Production process capability report
7.5 | ISO 26262-7, 5.5.5 | Safety-related content of the service plan | Objective acc. the standard ISO 26262-7: |  |  | No |  |  | Safety-related content of the service plan
7.6 | ISO 26262-7, 5.5.6 | Safety-related content of the service instructions | Objective acc. the standard ISO 26262-7: |  |  | No |  |  | Safety-related content of the service instructions
7.7 | ISO 26262-7, 5.5.7 | Safety-related content of the information made available to the user | Objective acc. the standard ISO 26262-7: |  |  | No |  |  | Safety-related content of the information made available to the user
7.8 | ISO 26262-7, 5.5.8 | Safety-related content of the decommissioning instructions | Objective acc. the standard ISO 26262-7: |  |  | No |  |  | Safety-related content of the decommissioning instructions
7.9 | ISO 26262-7, 5.5.9 | Operation, service and decommission requirements specification | Objective acc. the standard ISO 26262-7: |  |  | No |  |  | Operation, service and decommission requirements specification
7.10 | ISO 26262-7, 5.5.10 | Safety-related conent of the rescue services instructions | Objective acc. the standard ISO 26262-7: |  |  | No |  |  | Operation, service and decommission requirements specification
| ISO 26262-7 Clause 6 | Production
7.11 | ISO 26262-7, 6.5.1 | Control measures report | Objective acc. the standard ISO 26262-7: |  |  | No |  | Requirements specification for production, operation, service and decommissioning, Release for production report, Warning and degradation concept, included in the functional safety concept | Control measures report
7.12 | ISO 26262-7, 6.5.2 | Production process capability report | Objective acc. the standard ISO 26262-7: |  |  | No |  | see above | Production process capability report
| ISO 26262-7 Clause 7 | Operation, service and decommission
7.13 | ISO 26262-7, 7.5.1 | Field observation instructions | Objective acc. the standard ISO 26262-7: |  |  | No |  | see above | Field observation instructions
8 | ISO 26262-8 | Supporting processes
| ISO 26262-8 Clause 5 | Interfaces within distributed developments
8.1 | ISO 26262-8, 5.5.1 | Supplier selection report | Objective acc. the standard ISO 26262-8: The objective of this clause is to describe the procedures and to allocate associated responsibilities within distributed developments for items and elements. | Selecting a supplier, confirm that the supplier has capability and qualification conforming to functional safety standard. |  | No |  | See prerequisites of the relevant phases of the safety lifecycle for which the distributed development is carried out. | Supplier selection report
8.2 | ISO 26262-8, 5.5.2 | Development interface agreement (DIA) | Objective acc. the standard ISO 26262-8: see above | Tier1 shall prepare a DIA for the development with the OEM for the item (in collaboration with OEM) |  | No |  | The draft version of development interface agreement (DIA) (from external source); the supplier’s tender based on a request for quotation (RFQ) | DIA
8.3 | ISO 26262-8, 5.5.3 | Supplier's safety plan | Objective acc. the standard ISO 26262-8: see above |  |  | No |  |  | Supplier's safety plan
8.4 | ISO 26262-8, 5.5.4 | Functional safety assessment report | Objective acc. the standard ISO 26262-8: see above |  |  | No |  |  | Supplier's assessment safety report
8.5 | ISO 26262-8, 5.5.5 | Supply agreement | Objective acc. the standard ISO 26262-8: see above |  |  | No |  |  | Supplier's aupply agreement
| ISO 26262-8 Clause 7 | Configuration management
8.6 | ISO 26262-8, 7.5.1 | Configuration management plan | Objective acc. the standard ISO 26262-8: The first objective is to ensure that the work products, and the principles and general conditions of their creation, can be uniquely identified and reproduced in a controlled manner at any time. The second objective is to ensure that the relations and differences between earlier and current versions can be traced. | Preparation of a Configuration management plan for the project. |  | No |  | Safety plan, Applicable prerequisites of the relevant phases of the safety lifecycle where configuration management is planned or managed | Configuration management plan
| ISO 26262-8 Clause 8 | Change management
8.7 | ISO 26262-8, 8.5.1 | Change management plan | Objective acc. the standard ISO 26262-8: The objective of change management is to analyse and control changes to safety-related work products throughout the safety lifecycle. | Change management plan for the project. |  | No |  | Safety plan, Configuration management plan | Change management plan
8.8 | ISO 26262-8, 8.5.2 | Change request | Objective acc. the standard ISO 26262-8: see above | Change request for the project. |  | No |  | Safety plan, Configuration management plan | Change request
8.9 | ISO 26262-8, 8.5.3 | Impact analysis and change request plan | Objective acc. the standard ISO 26262-8: see above |  |  | No |  | Safety plan, Configuration management plan | Impact analysis and change request plan
8.10 | ISO 26262-8, 8.5.4 | Change report | Objective acc. the standard ISO 26262-8: see above |  |  | No |  | Safety plan, Configuration management plan | Change report
| ISO 26262-8 Clause 9 | Verification
8.11 | ISO 26262-8, 9.5.1 | Verification plan | Objective acc. the standard ISO 26262-8: The objective of verification is to ensure that the work products comply with their requirements. | Tier1 shall prepare a Verification plan for the project. |  | No |  | See applicable prerequisites of the relevant phases of the safety lifecycle in which verification is planned or carried out. | Verification plan
8.12 | ISO 26262-8, 9.5.2 | Verification specification | Objective acc. the standard ISO 26262-8: The objective of verification is to ensure that the work products comply with their requirements. |  |  | No |  | See applicable prerequisites of the relevant phases of the safety lifecycle in which verification is planned or carried out. | Verification specification
8.13 | ISO 26262-8, 9.5.3 | Verification report | Objective acc. the standard ISO 26262-8: The objective of verification is to ensure that the work products comply with their requirements. |  |  | No |  | See applicable prerequisites of the relevant phases of the safety lifecycle in which verification is planned or carried out. | Verification report
| ISO 26262-8 Clause 10 | Documentation Management
8.14 | ISO 26262-8, 10.5.1 | Documentation management plan | Objective acc. the standard ISO 26262-8: The primary objective is to develop a documentation management strategy for the entire safety lifecycle in order to facilitate an effective and repeatable documentation management process ent. |  |  | No |  | Safety plan, Project plan | Documentation management plan
|  |  |  | Objective for subsystem XYZ after tailoring: | Objective for subsystem XYZ after tailoring:
|  |  |  | Tier1 shall prepare a Documentation management plan for the project under developement. | Tier1 shall prepare a Documentation management plan for the project under developement.
8.15 | ISO 26262-8, 10.5.2 | Documentation guideline requirements | Objective acc. the standard ISO 26262-8: see above Objective for item under developement after tailoring: Documentation guideline requirements for the project. |  |  | No |  | Safety plan, Project plan | Documentation guideline requirements
| ISO 26262-8 Clause 11 | Confidence in the use of software tools
8.16 | ISO 26262-8, 11.5.1 | Software tool criteria evaluation report | Objective acc. the standard ISO 26262-8: The first objective of this clause is to provide criteria to determine the required level of confidence in a software tool when applicable. The second objective of this clause is to provide means for the qualification of the software tool when applicable, in order to create evidence that the software tool is suitable to be used to tailor the activities or tasks required by ISO26262 |  |  | No |  | Safety plan, applicable prerequisites of the phases of the safety lifecycle where a software tool is used. Evaluation plan of SW tools | software tool criteria evaluation report
8.17 | ISO 26262-8, 11.5.2 | Software tool qualification report | Objective acc. the standard ISO 26262-8: see above |  |  | No |  | Safety plan, applicable prerequisites of the phases of the safety lifecycle where a software tool is used. | software tool qualification report incl. Restrictions for use
| ISO 26262-8 Clause 12 | Qualification of software components
8.18 | ISO 26262-8, 12.5.1 | Software component documentation | Objective acc. the standard ISO 26262-8: |  |  | No |  |  | Software component documentation
8.19 | ISO 26262-8, 12.5.2 | Software component qualification report | Objective acc. the standard ISO 26262-8: |  |  | No |  |  | Software component qualification report
8.20 | ISO 26262-8, 12.5.3 | Software component qualification verification report | Objective acc. the standard ISO 26262-8: |  |  | No |  |  | Software component qualification verification report
| ISO 26262-8 Clause 13 | Qualification of hardware components
8.21 | ISO 26262-8, 13.5.1 | Hardware element evaluation plan | Objective acc. the standard ISO 26262-8: The first objective of the qualification of hardware components is to provide evidence of the suitability of intermediate level hardware components and parts for their use as part of items, systems or elements, developed in compliance with ISO 26262, concerning their functional behaviour and their operational limitations for the purposes of the safety concept. |  |  | No |  | Related safety requirements, Qualification criteria (analysis and tests) in accordance with ISO 26262-5:2018, Clause 6, The manufacturer's hardware component or part specification, or, if unavailable, the assumptions on hardware component or part specification (from an external source). | Qualification plan for hardware component (if applicable)
8.22 | ISO 26262-8, 13.5.2 | Hardware element test plan | Objective acc. the standard ISO 26262-8: The second objective of the qualification of hardware components is to provide relevant information regarding: - their failure modes, - their failure mode distribution, and - their diagnostic capability with respect to the safety concept for the item. |  |  | No |  | see above | Hardware component test plan (if applicable)
8.23 | ISO 26262-8, 13.5.3 | Hardware element evaluation report for hardware elements | Objective acc. the standard ISO 26262-8: see above |  |  | No |  | see above | Qualification report (if applicable)
| ISO 26262-8 Clause 14 | Proven in use
8.24 | ISO 26262-8, 14.5.1 | Description of candidate for proven in use argument | Objective acc. the standard ISO 26262-8: see above |  |  | No |  |  | Not applicable
8.25 | ISO 26262-8, 14.5.2 | Proven in use analysis reports | Objective acc. the standard ISO 26262-8: see above | e.g. analysis of field data to quality, faults, hazard events to evaluate the proven in use recommendations of ISO 26262. |  | No |  |  | Not applicable
9 | ISO 26262-9
ISO 26262-9 Clause 5
9.1 | ISO 26262-9, 5.5.1 | Update of architectural information | Objective acc. the standard ISO 26262-9: This clause provides rules and guidance for decomposing safety requirements into redundant safety requirements to allow ASIL tailoring at the next level of detail. Objective for item under developement after tailoring: ASIL decomposition is applied for ASIL D subsystem steering angel sensor. |  |  |  |  | The safety requirements at the | Update of architectural information
9.2 | ISO 26262-9, 5.5.2 | Update of ASIL as attribute of safety requirements and elements | Objective acc. the standard ISO 26262-9: see above |  |  |  |  | see above | Update of ASIL as attribute of safety requirements and elements
ISO 26262-9 Clause 6
9.3 | ISO 26262-9, 6.5.1 | Update of ASIL as attribute of sub-elements of elements | Objective acc. the standard ISO 26262-9: This clause provides criteria for the coexistence within the same element of: - safety-related sub-elements with sub-elements that have no ASIL assigned; and - safety-related sub-elements that have different ASILs assigned. Objective for item under developement after tailoring: ASIL decomposition is applied with different ASIL for different subsystems. |  |  |  |  | The safety requirements at the level at which the analysis is to be performed: system, or hardware, or software. The architectural information of the element at the level at which the analysis is to be performed: system, or hardware, or software. It's a refinement step during the design process. See ISO 26262-9, 6.4 | Update of ASIL as attribute of sub-elements of elements
ISO 26262-9 Clause 7
9.4 | ISO 26262-9, 7.5.1 | Analysis of dependent failures | Objective acc. the standard ISO 26262-9: The analysis of dependent failures aims to identify the single events or single causes that could bypass or invalidate a required independence or freedom from interference between given elements and violate a safety requirement or a safety goal. |  |  |  |  | The freedom from interference requirements at the level at which they are applied: system, or hardware, or software. The architectural information at the level at which the independence or freedom from interference requirements are to be applied: system, or hardware, or software. Analysis dependent/commmen cause failures. See ISO 26262-9, 7 | Analysis of dependent failures
9.5 | ISO 26262-9, 7.5.2 | Dependent Failures Analysis Verification Report | Objective acc. the standard ISO 26262-9:7.4.9
| ISO 26262-9 Clause 8 | Safety analyses
9.5 | ISO 26262-9, 8.5.1 | Safety analyses | Objective acc. the standard ISO 26262-9: The objective of safety analyses is to examine the consequences of faults and failures on the functions, behaviour and design of items and elements. Safety analyses also provide information on conditions and causes that could lead to the violation of a safety goal or safety requirement. Additionally, the safety analyses also contribute to the identification of new functional or non-functional hazards not previously identified during the hazard analysis and risk assessment. |  |  |  |  | The safety requirements at the level at which the safety analysis is to be performed: system, or hardware, or software. The architectural information of the element at the level at which the safety analysis is to be performed: system, or hardware, or software. The safety plan. | Safety analyses
9.5 | ISO 26262-9, 8.52 | Safety analyses verification report | Objective acc. the standard ISO 26262-9: 8.4.8 |  |  |  |  | Safety analyses | Safety analyses verification report
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on L7: Xiang: As far as the implementation differes from the responsible organisation it has to be stated by whom the Implementation/accomplishment relies on. There might be more than one named thus these can be named by adding rows. Partly filled with examples.

## Description of 3_Document_list
Safety Plan
1.Description to headlines of sheet "3_Document_list"
Part | Refering part of ISO26262
ISO 26262:2018 Work Products | Name of the work products
Reference to Safety Plan | The reference number to the data sheet 2_Safety_plan
initial/ refined | "Initial": Is the first version of a work product. In a real progress of a project the available information is not as datailed as at the end of a project which has to lead to a refinement of a document. "Refined": shows that a certain stage of a project a document with the appropriate information should already be available. "Refined" usually means in the corresponding phase of the project additions for the appropriate work product.
Link to external source | Search link to an external Data base (e.g. Doors) where the document/the information is stored. There might be multiple links if there are more than one external sources be needed. This should be done by adding rows.
Details to ext. Source | There should be information added to locate the needed information. With reference to: "Link to external source"
Index | Actual Index of the Source if applicable.
Title/chapter of comprised work product | Titel (if reasonable: Chapter) of the work product.
Todo's and Remarks | Short description to open issues and global remarks or aspects Intention is to comment the next column "Status".
Status | "Actual status of the issue Description of Status, see Table ""Description of Status"""
Date of Status | Date of given status
Responsible person: RASIC | Definition see RASIC table below.
Client/Dep. | This row is optional. Intention is to give a quick overview which client / department has which share on the project.
Milestone (Project Plan) | Refering milestone of the project plan Might be a gate in the developent process
Exchange of Data | Document/infomation which has to be exchanged to next responsible or counterpart of management or technique
Date sent | Date when the exchange was done.
2. Description of "RASIC"
RASIC symbol | Meaning | Definition
R | Responsible | Those who do the work to achieve the task. There is typically one role with a participation type of responsible, although others can be delegated to assist in the work required
A | Approver | The one ultimately answerable for the correct and thorough completion of the deliverable or task, and the one who delegates the work to those responsible. In other words, an accountable must sign off (approve) on work that responsible provides.
S | Support | Resources allocated to responsible. Unlike consulted, who may provide input to the task, support will assist in completing the task.
I | Informed | Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication
C | Consulted | Those whose opinions are sought, typically subject matter experts; and with whom there is two-way communication.
3. Sample use status
Sample | Meaning
A-Sample | The A-Sample shall be used for the presentation of  Concepts  Critical functions  Technology assessments  the sample is only for restricted use
B-Sample | The B-Samples are  Develop samples for technology-critical details, such as function, design, and assembly.  Samples used to uncover emergent product requirements  the samples may have use restrictions
C-Sample | The C-Samples are samples provide further test, development, and validation and are near-series samples. The C-Samples fulfill all specified safety and non-safety requirements. The Sample have no use restrictions.
Initial Sample | The initial sample is the first production falling part that was manufactured ​​on the final production plant.

## Tabelle1 (hidden)
Status
open
in progress
in review
reviewed
approved
released
not applicable